## Basic Gantt Chart
TASKS | Competency needed | Cost per person per month | Number of months | Cost | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3 | [11 empty] | YEAR 4
VOCALEX |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Research | bar: YEAR 1 1 to YEAR 2 13; YEAR 2 16; YEAR 2 21; YEAR 3 25; YEAR 3 27; YEAR 3 29
Market analysis | Market analyst | 3333 | 3 | 9999 | bar: YEAR 1 1 to YEAR 1 3
Target audience | UX researcher | 1700 | 4 | 6800 | bar: YEAR 1 1 to YEAR 1 4
Speaker | Acoustic engineer | 3360 | 2 | 6720 | bar: YEAR 1 4 to YEAR 1 5
Wearable materials for speaker | Industrial Designer | 2161 | 2 | 4322 | bar: YEAR 1 4 to YEAR 1 5
In-house testing |  |  | 11 | 0 | bar: YEAR 1 6 to YEAR 1 7; YEAR 1 10 to YEAR 2 13; YEAR 2 16; YEAR 2 21; YEAR 3 25; YEAR 3 27; YEAR 3 29
Ideation | bar: YEAR 1 4 to YEAR 1 5
Design | bar: YEAR 1 4 to YEAR 2 15
Hardware | bar: YEAR 1 4 to YEAR 1 6; YEAR 1 8 to YEAR 1 9
Wireframe | Graphic designer, industrial designer | 2161 | 8 | 17288 | bar: YEAR 1 4 to YEAR 1 5
3D Mockup - button position, material selection, speaker position |  | 1871 | 6 | 11226 | bar: YEAR 1 5 to YEAR 1 6; YEAR 1 8 to YEAR 1 9
Software | bar: YEAR 1 4 to YEAR 1 10; YEAR 2 14 to YEAR 2 15
UI Wireframes | Graphic designer, software engineer | Counted above | bar: YEAR 1 4 to YEAR 1 5
Interactive prototype |  | 2609 | 5 | 13045 | bar: YEAR 1 6 to YEAR 1 8
Conversation design - Emotive options, context driven predictive text, keyboard options for personalization | Computational linguist | 3273 | 8 | 26184 | bar: YEAR 1 5 to YEAR 1 10; YEAR 2 14 to YEAR 2 15
Development | bar: YEAR 1 5 to YEAR 3 36
Hardware | bar: YEAR 2 14 to YEAR 2 17; YEAR 2 21; YEAR 3 35
Feasibility prototype | Acoustical engineer, industrial designer | 3360 | 6 | 20160 | bar: YEAR 2 14 to YEAR 2 15
Live prototype |  | 2161 | 6 | 12966 | bar: YEAR 2 16 to YEAR 2 17; YEAR 2 21; YEAR 3 35
Software | Computer scientist, software engineer, data scientist, UI/UX developer | 6360 | 18 | 114480 | bar: YEAR 1 5 to YEAR 3 36
Feasibility prototype |  | 2609 | 64 | 166976 | bar: YEAR 1 12 to YEAR 2 18
Live prototype |  | 2900 | 32 | 92800 | bar: YEAR 2 23 to YEAR 3 31; YEAR 3 35
AI |  | 2279 | 17 | 38743 | bar: YEAR 1 5 to YEAR 3 36
Testing | bar: YEAR 2 19 to YEAR 2 21; YEAR 2 24; YEAR 3 29 to YEAR 3 36
Controlled environment | UX researcher, Beta Users | 1700 | 7 | 11900 | bar: YEAR 2 19 to YEAR 2 21; YEAR 2 24; YEAR 3 29 to YEAR 3 31
In the wild - end users testing | End Users | 400 | 62 | 24800 | bar: YEAR 3 32 to YEAR 3 36
Manufacturing and production |  |  | Units | bar: YEAR 2 18 to YEAR 2 20; YEAR 2 22 to YEAR 3 33
Commerical Prototype of Vocalex Speaker | Outsourcing | 42 | 2 | 84 | bar: YEAR 2 18 to YEAR 2 20
Scaled Production |  | 22 | 1000 | 22000 | bar: YEAR 2 22 to YEAR 3 33
Quality assurance and certification | bar: YEAR 2 21
Compliance Evaluation with EMA | EMA compliance specialist | 3833 | 1 | 3833 | bar: YEAR 2 21
Marketing | bar: YEAR 1 5; YEAR 2 14; YEAR 2 20; YEAR 3 25 to YEAR 4 38
Branding- visuals | Marketing manager | 3639 | 18 | 65502 | bar: YEAR 1 5; YEAR 3 25 to YEAR 3 36
Pricing | Sales manager, product manager, Marketing manager | 5000 | 6 | 30000
|  | 3333 | 6 | 19998 | bar: YEAR 2 14; YEAR 2 20; YEAR 3 30 to YEAR 3 33
Promotion - content creation, ads, website | Marketing manager | Already counted above | bar: YEAR 3 32 to YEAR 3 33; YEAR 3 36 to YEAR 4 38
AWS Cloud Database Fee
Google Text-to-Speech Fee
Project Management
|  |  | Total | 719826

## Copia di Basic Gantt Chart
TASKS | Competency needed | Cost per person per month | Number of months | Cost | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3 | [11 empty] | YEAR 4
VOCALEX |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Research | bar: YEAR 1 1 to YEAR 2 13; YEAR 2 16; YEAR 2 21; YEAR 3 25; YEAR 3 27; YEAR 3 29
Market analysis | Market analyst | 3333 | 3 | 9999 | bar: YEAR 1 1 to YEAR 1 3
Target audience | UX researcher | 1700 | 4 | 6800 | bar: YEAR 1 1 to YEAR 1 4
Speaker | Acoustic engineer | 3360 | 2 | 6720 | bar: YEAR 1 4 to YEAR 1 5
Wearable materials for speaker | Industrial Designer | 2161 | 2 | 4322 | bar: YEAR 1 4 to YEAR 1 5
In-house testing |  |  | 11 | 0 | bar: YEAR 1 6 to YEAR 1 7; YEAR 1 10 to YEAR 2 13; YEAR 2 16; YEAR 2 21; YEAR 3 25; YEAR 3 27; YEAR 3 29
Ideation | bar: YEAR 1 4 to YEAR 1 5
Design | bar: YEAR 1 4 to YEAR 2 15
Hardware | bar: YEAR 1 4 to YEAR 1 6; YEAR 1 8 to YEAR 1 9
Wireframe | Graphic designer, industrial designer | 2161 | 8 | 17288 | bar: YEAR 1 4 to YEAR 1 5
3D Mockup - button position, material selection, speaker position |  | 1871 | 6 | 11226 | bar: YEAR 1 5 to YEAR 1 6; YEAR 1 8 to YEAR 1 9
Software | bar: YEAR 1 4 to YEAR 1 10; YEAR 2 14 to YEAR 2 15
UI Wireframes | Graphic designer, software engineer | Counted above | bar: YEAR 1 4 to YEAR 1 5
Interactive prototype |  | 2609 | 5 | 13045 | bar: YEAR 1 6 to YEAR 1 8
Conversation design - Emotive options, context driven predictive text, keyboard options for personalization | Computational linguist | 3273 | 8 | 26184 | bar: YEAR 1 5 to YEAR 1 10; YEAR 2 14 to YEAR 2 15
Development | bar: YEAR 1 5 to YEAR 3 36
Hardware | bar: YEAR 2 14 to YEAR 2 17; YEAR 2 21; YEAR 3 35
Feasibility prototype | Acoustical engineer, industrial designer | 3360 | 6 | 20160 | bar: YEAR 2 14 to YEAR 2 15
Live prototype |  | 2161 | 6 | 12966 | bar: YEAR 2 16 to YEAR 2 17; YEAR 2 21; YEAR 3 35
Software | Computer scientist, software engineer, data scientist, UI/UX developer | 6360 | 18 | 114480 | bar: YEAR 1 5 to YEAR 3 36
Feasibility prototype |  | 2609 | 64 | 166976 | bar: YEAR 1 12 to YEAR 2 18
Live prototype |  | 2900 | 32 | 92800 | bar: YEAR 2 23 to YEAR 3 31; YEAR 3 35
AI |  | 2279 | 17 | 38743 | bar: YEAR 1 5 to YEAR 3 36
Testing | bar: YEAR 2 19 to YEAR 2 21; YEAR 2 24; YEAR 3 29 to YEAR 3 36
Controlled environment | UX researcher, Beta Users | 1700 | 7 | 11900 | bar: YEAR 2 19 to YEAR 2 21; YEAR 2 24; YEAR 3 29 to YEAR 3 31
In the wild - end users testing | End Users | 400 | 62 | 24800 | bar: YEAR 3 32 to YEAR 3 36
Manufacturing and production |  |  | Units | bar: YEAR 2 18 to YEAR 2 20; YEAR 2 22 to YEAR 3 33
Commerical Prototype of Vocalex Speaker | Outsourcing | 42 | 2 | 84 | bar: YEAR 2 18 to YEAR 2 20
Scaled Production |  |  | 1000 | bar: YEAR 2 22 to YEAR 3 33
Quality assurance and certification | bar: YEAR 2 21
Compliance Evaluation with EMA | EMA compliance specialist | 3833 | 1 | 3833 | bar: YEAR 2 21
Marketing | bar: YEAR 1 5; YEAR 2 14; YEAR 2 20; YEAR 3 25 to YEAR 4 38
Branding- visuals | Marketing manager | 3639 | 18 | 65502 | bar: YEAR 1 5; YEAR 3 25 to YEAR 3 36
Pricing | Sales manager, product manager, Marketing manager | 5000 | 6 | 30000
|  | 3333 | 6 | 19998 | bar: YEAR 2 14; YEAR 2 20; YEAR 3 30 to YEAR 3 33
Promotion - content creation, ads, website | Marketing manager | Already counted above | bar: YEAR 3 32 to YEAR 3 33; YEAR 3 36 to YEAR 4 38
AWS Cloud Database Fee
Google Text-to-Speech Fee
|  |  | Total | 697826

## Manual Chart (hidden)
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 2 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 4 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 3 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 2 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 4 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 4 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 8 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 4 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 4 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 4 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 3 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 4 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 2 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 4 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 3 | Rachel | 40%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])